UoB CCI Project Plan
What has been completed by 17th March 2020:
1. Prototype lessons for the following have been produced on a Jupyter Notebook:
  1. O1A
    1. Section 1: Introduction to the Pandas library
    2. Section 2: What does open source mean?
    3. Section 3: .csv files
    4. Section 4: Applications of Python programming in Business. Which covers the following points:
      1. Artificial Intelligence and Machine Learning
      2. Big Data and its applications
    5. Summary of the points covered in section 4 and explaining why it is important for students to learn how to program.
  2. O1B
    1. Lesson 1: Input and Output
    2. Lesson 2: Manipulation of Data
    3. Lesson 3: Graphs
    4. Lesson 4: Descriptive Statistics – This lesson has been given to our Spanish partners and they will complete development of it
Plan from April 2020 onwards:
1. Develop a working environment in Bitbucket
2. O1A specific goals:
  1. Add short summaries at the end of each section which collate all that is taught.
  2. Provide pointers to resources should the students want to extend their studies at the end of each section
  3. Develop learning objective at the start of each section. Making clear what the students will be required to know in order to complete the questions
  4. Complete developing AI and Big Data sections with informative diagrams which will help to provide clear and concise descriptions.
  5. Develop a demonstration of Machine Learning, maybe graphical with the bokeh package.
  6. Rework wordy sections so that all information is concisely understood in clear English for a complete beginner.
  7. Add source / citations to the appropriate location of information and data
  8. Reword the introduction to DataFrames
  9. Include more graphics and demonstrations
3. O1B specific goals:
  1. Add short summaries at the end of each section which collate all that is taught.
  2. Add short conclusions that include all the functions and concepts the students should be able to wield before they start the questions
  3. Add more description and explanation in all lessons
  4. Develop more interactive modes which let the students experiment and learn with the programs
  5. Rework wordy sections so that all information is concisely understood in clear English for a complete beginner.
  6. Add source / citations to the appropriate location of information and data
  7. Provide direction and links should the students what to extend their own education
  8. Lesson 1:
    1. Show df[“New Column title”] = SERIES as a way to insert a column
    2. Include more information on coordination of eg: [:-1], finding specifically named rows
  9. Provide a graphic in Lesson 2 which shows what a pivot table does. See https://pandas.pydata.org/docs/user_guide/reshaping.html
  10. Lesson 3: use the iris dataset for the histogram section. Saving the recorded data for the questions. Which can be downloaded in the program from here https://raw.githubusercontent.com/jbrownlee/Datasets/master/iris.csv
  11. Consider the possibilities of uploading .csv files to github/bitbucket and downloading them and opening them in program

1. O2 specific goals:
  1. Develop 5 questions for O1A
  2. Develop the remaining questions (5 question per lesson) for O1B
  3. Test all questions when all complete.
  4. Research how an automatic grading system could be integrated into these (O3)